No.BB/Colleges/2011-12/Vol-II/38            dt at Chennai-8 the    02-03-2012

To

All SSA Heads,

BSNL,TN Circle.

Sub: NMEICT Project –Slow provision of VPNoBB connections - reg.

Ref: This Off.Lr.No.BB/Colleges/2011-12/Vol-II/19    dt.24-01-2012.

Since CGM,TN Circle is reviewing the progress of VPNoBB connections provided to the colleges under NMEICT Project every week, vide above reference it was requested  to  visit all the pending colleges and provide the connections for all feasible cases immediately through ADSL/WiMAX/FTTF technology in order to  complete the project before Mar-12  &  to update the NME- online internet web site  http://59.90.240.104/ssanme  on the  last working day of every week.

From the on-line reports by SSAs in the above said internet web site, for the periods from 31-01-2012 to 25-02-2012 (SSA Wise details  attached ), it is found that not even  a single connection have been provided by the SSAs except Pondicherry, Salem, Trichy and Thirunelveli SSAs.

Hence SSA Heads are requested to bestow personal attention to achieve the already assigned target  before Mar-12. It is also requested to make the online updation on the last working day of every week positively.

Sd/-

Encl:  As above      					         Dy.General Manager (NWP-CFA),

O/o PGM-CFA,

BSNL,Tamilnadu Circle,

Chennai-8.

NMEICT-COLLEGES-VPNoBB PROVISION STATUS ( As per online & oral report by SSAs)

| SL.NO. | SSA | Grand Total No.of NMEICT colleges | As on 31-1-2012 |  | As on 25-2-2012 |  | Achievement for the period from 31-01-2012 to 25-02-2011 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Domain Created ( No.of colleges connected) | VPNoBB Connection Provided | Domain Created ( No.of colleges connected) | VPNoBB Connection Provided | Domain Created ( No.of colleges connected) | VPNoBB Connection Provided |
| 1 | CBE | 256 | 56 | 576 | 56 | 576 | 0 | 0 |
| 2 | CDL | 146 | 24 | 64 | 24 | 64 | 0 | 0 |
| 3 | CON | 14 | 6 | 56 | 6 | 56 | 0 | 0 |
| 4 | DPI | 91 | 9 | 71 | 9 | 71 | 0 | 0 |
| 5 | ERD | 74 | 22 | 149 | 22 | 149 | 0 | 0 |
| 6 | KKD | 84 | 23 | 220 | 23 | 220 | 0 | 0 |
| 7 | KMB | 89 | 20 | 162 | 20 | 162 | 0 | 0 |
| 8 | MA | 218 | 47 | 222 | 47 | 222 | 0 | 0 |
| 9 | NGC | 112 | 18 | 63 | 18 | 63 | 0 | 0 |
| 10 | PY | 81 | 18 | 247 | 22 | 309 | 4 | 62 |
| 11 | SLM | 243 | 48 | 300 | 51 | 325 | 3 | 25 |
| 12 | TNJ | 93 | 12 | 86 | 12 | 86 | 0 | 0 |
| 13 | TR | 279 | 69 | 581 | 75 | 647 | 6 | 66 |
| 14 | TT | 50 | 12 | 113 | 12 | 113 | 0 | 0 |
| 15 | TVL | 105 | 40 | 311 | 40 | 315 | 0 | 4 |
| 16 | VGR | 54 | 9 | 85 | 9 | 85 | 0 | 0 |
| 17 | VLR | 196 | 18 | 148 | 18 | 148 | 0 | 0 |
|  | Total | 2185 | 451 | 3444 | 464 | 3611 | 13 | 167 |